## Road Map
QUICK BOOK
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 10/25/2024 | SPRINT2 - 11/13/2024 | SPRINT3 - 12/15/2024
01.Venue Management | 01.01Account Authentication/Modification Tell me what you want to do 12 General C2 01.01 Account Authentication/Modification Functional Decomposition RTM 100% | 5 | X
| 01.02Venue search | 3 | X
| 01.03 Seat booking/availability | 5 | X
02. Customer support | 02.01Feedback and Surveys | 3
| 02.02Issue tracking system | 3 |  | X
| 02.03Ticketing System | 5 |  | X
| 02.04Submit rating | 3
| 02.05 Post Review | 5
03. Advertising | 03.01 Post Ad Tell me what you want to do 12 General K2 03.01 Post Ad Functional Decomposition RTM Crosscut Description RCT Details Feature Short Description ET-Entitlements 100% | 3 |  |  | X
| 03.02 Update Ad | 3
| 03.03 Remove Ad | 3
04. Payment | 04.01 Payment Methods | 5 |  |  | X
| 04.02 Payment Validation General O2 04.02 Payment Validation | 5 |  |  | X
| 04.03 Split Payments among users | 4
| 04.04 Installment Payments | 4
05. Email/Notifications | 05.01 Notification delivery status | 5 |  | X
| 05.02 Subscription renewal alert | 4
| 05.03 Refund Process Notification | 3 |  |  | X
| 05.04 Promotional Emails | 4
|  | VELOCITY: | 13 | 13 | 16
s